## 09-18 to 09-21 2018
Task | Module | Status | Path
Add comment/remarks for cancelling MPR | View MPR | Done | My Account > My MPR > My MPR List > view MPR
Show status and comment in update MPR | View MPR | Done | My Account > My MPR > My MPR List > view MPR
Show approver in My MPR List table when status is active | My MPR List | Done | My Account > My MPR > My MPR List
Show approver in My Team's MPR table when status is active | My Team's MPR | Done | My Account > My MPR > My Team's MPR
Filters on all MPR's list. i.e MPR id, Reference Id | My Team's MPR, My MPR, Finance Pending Approval, MPR (under HR module) | For checking | -
Add 'View applicant' module in My MPR List | View Applicant | For checking | My Account > My MPR > My MPR List > View Applicant
Add logs for log in failed | Login | For checking | Login
Add number of attempts in log in. Disable user if maximum attempt is reached. | Login | For checking | Login
Record logs for log out | Login | On development | Login
Create report for log in / log out logs (Export to excel file ) | Login | On queue | Login